CABE COMPASS

ACTION PLAN

|  |  |
| --- | --- |
| Cardinal Point #4 | Accountability for Success |
| Claim/Goal #4.3 | **Chapter Engagement:** Design and roll out a professional development strategy for engaging CABE chapters in effectively and compellingly understanding, communicating, and enacting the CABE COMPASS accountability provisions.  |
| Actions | How (Specific Steps) | Timeline | Person(s) Responsible | Needed Resources | Measures of Success & Quality |
| 4.3.1 Train all regional representatives and chapter officers in the CABE COMPASS and its accountability provisions, and the use of the CABE resources and materials. | * Develop a facilitator’s agenda and PowerPoint.
* Establish a training schedule that includes dates, locations, audiences, and presenters.
* Work with CABE staff to prepare/deliver the training materials to each presenter/site.
* Conduct the training.
* Conduct a six-month follow up monitoring to assess how well those trained are implementing what they learned in the training.
 | Spring /Summer 2014 | Jan GustafsonTrainers TBDCABE Board Members | Training FacilityCopies of the MaterialsFacilitator’s Agenda & PPT | 90% of Regional Reps and Chapter Officers TrainedResults of Follow Up Monitoring Demonstrate that Minimally 75% of Those Trained Are Implementing the Training |
| 4.3.2 Create and use marketing collateral featuring the CABE COMPASS’s accountability provisions and CABE’s related services. | * Work with a marketing consultant and graphic designer to develop the marketing collateral.
* Develop a facilitator’s agenda and PowerPoint to train all chapter leaders in marketing CABE COMPASS accountability provisions and services.
* Establish a training schedule that includes dates, locations, audiences, and presenters.
* Work with CABE staff to prepare/deliver the training materials to each presenter/site.
* Conduct the training.
 | Fall/Winter 2014 | Jan Gustafson-CoreaPaul FloresTrainers TBDMedia Consultant (Pro Bono?) | Budget and Sources of New RevenueFocus GroupsCopies of the Marketing CollateralFacilitator’s Training Agenda & PPT | Collateral Developed90% of Chapter Leaders Trained |
| 4.3.3 Create media spots to showcase the CABE COMPASS’s accountability provisions and CABE’s new services in support of accountability. | * Work with a communications expert to develop and place the media spots.
 | Fall/Winter 2014 | Jan Gustafson-CoreaMedia Consultant (Pro Bono?) | Budget and Sources of New Revenue | Media Spots Developed & Placed |