CABE COMPASS

ACTION PLAN

| Cardinal Point #4 | Accountability for Success |
| --- | --- |
| Claim/Goal #4.6 | Budget & Fund Development: Develop multi-year budget and fund development plans to help the staff and board set realistic income goals with respect to the annual budgeting process and implementation of the CABE COMPASS; outline the strategic steps required to reach those goals, as well as board and staff responsibilities in accomplishing the plans; and identify targeted financial and strategic goals necessary to support successful COMPASS implementation. |
| Actions | How (Specific Steps) | Timeline | Person(s) Responsible | Needed Resources | Measures of Success & Quality |
| 4.6.1 Establish budgets, budget strategy, and fund development goals for all COMPASS action plans. | Work with action plan leads and staff to develop a budget for each action plan. Determine the necessary fund development goals and strategies to support each budget. Identify board and staff fund development responsibilities. Identify targeted financial goals necessary to support the action plans. Revise and update the goals/plan on an as-needed basis in conjunction with revisions to the operating budget. | July 2013 and Ongoing | Jan Gustafson-Corea Director of Business Services Director of Financial Affairs | Fund Development Consultant (In Kind) Fund Development Start Up Budget | Balanced Annual Budget Five-Year Budget and Fund Development Plans 90% of Fund Development Goals Achieved |
| 4.6.2 Establish a system of contract development, management, and monitoring. | Identify staff lead(s) for contract management. Establish and maintain a system to manage current contracts. Develop a plan to increase contracts by at least 10%. Evaluate customer satisfaction with CABE contract services. | July 2013 and Ongoing | Jan Gustafson-Corea Director of Business Services | Staff | 10% Increase in Contract Revenue 90% Customer Satisfaction |
| 4.6.3 Establish a system of fund solicitation strategies. | Develop a COMPASS synthesis to use in fund solicitation and cultivation. Establish personal solicitation plans, special fund development events, direct mail campaigns, and government and foundation grant applications. Engage Board members, executive director, and key staff in a giving program. Engage Board members in fundraising tasks, including cultivation of donors/sponsors. Develop and implement an enhanced communications plan re: fund development within the board and with prospects, including regular presentations at board meetings by fund development chair. Develop plan for ongoing recruitment/training of fundraising volunteers. Recruit a minimum of ten non-board volunteers to work in fund development. Develop new prospects for both personal solicitation campaign and direct mail solicitation; cultivate family foundations/trusts. | September 2013 and Ongoing | Jan Gustafson-Corea Director of Business Services Director of Financial Affairs | Fund Development Consultant (In Kind) Fund Solicitation Start Up Budget | Five-Year Fund Solicitation Plan 90% of Fund Solicitation Goals Achieved |
| 4.6.4 Develop a portfolio of cultivation strategies (“making friends”). | Strengthen donor cultivation program and board and staff understanding of the purpose and process of cultivation. Actively involve staff in special events and fundraising activities. Design and implement a calendar of open houses and communications to add prospects to CABE’s donor base and develop them to become active supporters and regular donors; and to improve relationships with current board members, donors, volunteers, and other friends of CABE to build a greater understanding of how they can help CABE achieve its mission. | September 2013 and Ongoing | Jan Gustafson-Corea Director of Business Services Director of Financial Affairs | Fund Development Consultant (In Kind) Fund Cultivation Start Up Budget | Five-Year Fund Cultivation Plan 90% of Fund Cultivation Goals Achieved |
| 4.6.5 Conduct an annual membership drive to increase membership. | Design the parameters of the membership drive, including incentives for different levels of membership solicitation: individual, institutional, chapter, regional. Launch the membership drive in October 2013 and each October thereafter. | October 2013 and Ongoing | Jan Gustafson-Corea Director of Business Services Director of Financial Affairs | TBD | Membership Drive Parameters 10% Annual Increase in Individual Memberships 10% Annual Increase in Institutional Memberships |
| 4.6.6 Maintain, monitor, and evaluate the budgeting and fund development plan and process. | Establish a budget and fund development committee that meets 6 times a year to review the progress of the plan and, with development staff, identifies problems and solutions. Establish a budget and fund development calendar. Add a standing fund development update item to the board agendas. Establish a process/protocol for development staff to provide financial and statistical data with which to help evaluate progress of the plan. Strengthen coordination between the public relations and fund development committees to further support fundraising efforts. Maintain systems for ongoing monitoring/evaluation of progress in all areas of budget and fund development. | October 2013 and Ongoing | Jan Gustafson-Corea Director of Business Services Director of Financial Affairs | TBD | Established Calendars Timelines Met 90% of Goals Met |